## Sheet1
GANTT CHART
TASK NAME | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8
| S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
Brainstorm | bar: WEEK 1 S to WEEK 1 W
Develope Design Matrix | bar: WEEK 1 W to WEEK 1 R
Do Background Research | bar: WEEK 1 S to WEEK 1 F; WEEK 2 M to WEEK 2 W; WEEK 3 M to WEEK 3 T
Define the Problem | bar: WEEK 1 T to WEEK 1 R
Produce Solution | bar: WEEK 1 W to WEEK 1 F
Produce Requirements List | bar: WEEK 1 W to WEEK 1 F
Create L0 diagram | bar: WEEK 1 R to WEEK 1 F
Create L1 diagram | bar: WEEK 1 F to WEEK 2 M
Develop Bill of Materials | bar: WEEK 2 M to WEEK 3 S
Create Gantt Chart | bar: WEEK 1 R to WEEK 1 F
Create hand-washing reminder | bar: WEEK 3 S to WEEK 4 S
Create CAD/Inventor Model of overall product, along with interior hardware
Create code for this feature
Test prototype reminder feature
12 hour and 24 hour function
Create timer for washing time | bar: WEEK 5 M to WEEK 6 F
create code for timing function of 20 seconds
decide on timer activation method
create code for activation method
add on to circuit build
test the code on prototype
create code for vibration sensor
Research notification options/how to
Sync this time data to a device/ transmit to cloud
Update Trello Status | bar: WEEK 1 T; WEEK 2 T; WEEK 3 T; WEEK 4 T; WEEK 5 T; WEEK 6 T; WEEK 7 T; WEEK 8 T
Backlog Check | bar: WEEK 1 T; WEEK 2 T; WEEK 3 T; WEEK 4 T; WEEK 5 T; WEEK 6 T; WEEK 7 T; WEEK 8 T
Develop Prototype | bar: WEEK 3 R to WEEK 3 S; WEEK 5 R to WEEK 5 S; WEEK 7 R to WEEK 7 S
Sprints | bar: WEEK 3 S to WEEK 4 R; WEEK 5 S to WEEK 6 R; WEEK 7 S to WEEK 8 F
Test Results | bar: WEEK 3 M to WEEK 3 F; WEEK 5 M to WEEK 5 F; WEEK 7 M to WEEK 7 F
Collect & communicate data from group | bar: WEEK 2 R to WEEK 3 F; WEEK 4 F to WEEK 5 F; WEEK 6 F to WEEK 7 F
Final Report | bar: WEEK 8 S to WEEK 8 S
Final Presentation | bar: WEEK 8 S to WEEK 8 R
Scheduled Team Meetings | bar: WEEK 1 M to WEEK 1 S; WEEK 2 T; WEEK 2 R; WEEK 2 S; WEEK 3 T; WEEK 3 R; WEEK 3 S; WEEK 4 T; WEEK 4 R; WEEK 4 S; WEEK 5 T; WEEK 5 R; WEEK 5 S; WEEK 6 T; WEEK 6 R; WEEK 6 S; WEEK 7 T; WEEK 7 R; WEEK 7 S; WEEK 8 T; WEEK 8 R
Create, test and fix Prototype (add/remove features as needed) | bar: WEEK 7 S to WEEK 8 F
create code for LED and Buzzer alarm system | bar: WEEK 3 F to WEEK 4 S
build the circuitry | bar: WEEK 4 M to WEEK 5 W; WEEK 7 S to WEEK 8 F
Test prototype reminder feature | bar: WEEK 4 M to WEEK 5 W; WEEK 7 S to WEEK 8 F